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Covering instruction from the lender to its LTA
Please extend your appointment for [Project] to include the readiness scope in this addendum. Where your existing scope already covers a readiness criterion, identify it so that work is not duplicated. Please confirm within [10] Business Days how you propose to deliver the scope, including any specialist support, the additional effort, and any limitation on evidence access.
This addendum forms part of the appointment of [LTA] (the Adviser) by [Agent / Lenders] (the Client) dated [date] for [Project] (the Appointment). Where this addendum and the Appointment conflict, the Appointment prevails on fees, liability, reliance, confidentiality and limitation, and this addendum prevails on the content of the readiness services. It adds to the Adviser's existing technical due diligence and monitoring; it does not change them.
1. Objective
The Adviser shall assess, from before financial close until the end of the agreed stabilization period, whether systems completion and operational readiness are maturing at the pace needed for the planned transition from construction to operations and for the operating performance assumed in the financing case, and whether the governance overseeing that transition is in place and working. The Adviser shall report its findings in a separately identifiable readiness section of its reports. The Adviser shall not represent that readiness maturity guarantees a successful outcome.
2. Reference framework
The readiness mandate is fulfilled against the ICxA Standards. The Outcome Assurance standards (ICXA-10000 to ICXA-10003) define the governance of the transition: outcome stage-gates, the evidence each requires, and the separation of evidence production, independent evaluation and authorization. The Commissioning & Outcome Execution standards (ICXA-20100 to ICXA-20103) define systems completion: the system breakdown, execution stage-gates and the minimum evidence for each. The Operational Readiness standards (ICXA-20200 to ICXA-20203) define the readiness of the receiving organization across People, Organization, Asset and Systems & Processes, the readiness reviews, and Transfer of Operational Control.
Each project defines its own stage-gates, readiness criteria and readiness conditions under those Standards. The Adviser assesses the project against what the project has defined and against the readiness criteria in Schedule 1, and reports where the project's arrangements fall short of the Standards. Figure 1 shows an example of how the pieces link.
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Figure 1. Example sequence linking the project's stage-gates, the lender's milestones and what the lender requires. Each project defines its own stage-gates, readiness criteria and readiness conditions under the ICxA Standards.
3. Definitions
1. Readiness means the demonstrated state in which the capabilities, arrangements and conditions required for the intended operational transition are sufficiently established to support the intended operation, with material residual risks understood and appropriately controlled. It does not require every activity to be complete or every deficiency to be closed. For an authorization decision, readiness is the condition in which sufficient evidence is available for that decision (ICXA-10000 cl. 3.11). Operational Readiness is the receiving organization's integrated capability to receive, operate, maintain and sustain the asset (ICXA-20202 entry 3.8).
1. Readiness maturity means the progressive development of readiness evidence and capability across the lifecycle, from identifying what readiness requires to demonstrating it (ICXA-20200 cl. 4.6 and 5.9). Low maturity early in a project is expected; the risk is the absence of evidence that readiness is maturing.
1. Readiness criteria means the defined expectations, requirements, thresholds or decision rules, set before the evidence is produced, against which the state of a readiness condition is judged for a stage-gate or readiness decision (ICXA-10001 cl. 6.3 e); ICXA-20201 cl. 6.7 and 8.1). The criteria the lender requires the LTA to assess are listed in Schedule 1.
1. Readiness conditions means the observable or assessable aspects of operational capability, preparedness or transition capability, such as required operator competence or critical deficiency status, that must be in the required state before progression through a stage-gate, a readiness recommendation, or Transfer of Operational Control (ICXA-20202 entry 3.20; ICXA-10001 cl. 6.3 d); ICXA-20101 cl. 9.3). A readiness activity, such as training or a turnover review, is the means of developing a condition and is not itself evidence that the condition exists.
1. Condition state means the assessed status of a readiness condition at a defined point in time or stage-gate, determined from the evidence against the applicable readiness criteria.
1. Evidence confidence means the degree of confidence that can reasonably be placed in the evidence supporting a condition state, having regard to its provenance, currency, completeness, relevance, independence, consistency and auditability. An asserted state without sufficient supporting evidence is not treated as demonstrated.
1. Stage-gate means a decision point defined by the project at which readiness is evaluated before progression: outcome stage-gates under ICXA-10001 cl. 6.3 and execution stage-gates for systems completion under ICXA-20101 cl. 9.2.
1. Systems completion means the completion, verification and handover of the asset by defined system boundaries, rather than by area or contract, so that each system can be shown ready before it is started up and transferred (ICXA-20101 cl. 7 and 9).
1. Outcome Evidence Need means the evidence required for each stage-gate, defined in advance and proportionate to consequence (ICXA-10002 cl. 4 to 6).
1. Transfer of Operational Control means the formal transfer of authority to operate a defined system from the delivery organization to the receiving organization (ICXA-20102; ICXA-20201 cl. 9.1).
1. Readiness Maturity Path means the project-specific statement, agreed by the lenders before financial close, of the stage-gates the project has defined, the readiness criteria and readiness conditions that apply at each, and any dated Readiness Milestones.
1. Readiness Milestone means a date in the Readiness Maturity Path by which specified readiness conditions must be demonstrated against their criteria.
1. Capital-release conditions means the conditions in the financing documents that the lenders have chosen to link to readiness findings. They are distinct from the project's readiness conditions.
1. Material Readiness Deficiency means a confirmed deficiency against a readiness criterion that the Readiness Maturity Path designates as material.
1. Readiness Material Change means a change to scope, technology, contracting structure, operator, operating model, system boundaries, schedule logic or operating assumptions that may affect a material readiness criterion.
4. Scope of assessment
The Adviser shall assess the readiness criteria in Schedule 1, which are grouped in six areas:
1. Outcome and financial alignment: whether the operating outcomes and assumptions in the financing case are defined and traceable, and whether construction completion, start-up, Transfer of Operational Control, commercial operation and the financing completion date are distinguished and connected.
1. Integrated delivery and interface accountability: whether responsibilities and interfaces across the EPC contractors, suppliers, owner and operator are allocated, and whether readiness decisions are made by people independent of delivery, as the Standards require (ICXA-10001 cl. 5.3; ICXA-20101 cl. 6.2; ICXA-20201 cl. 5.2).
1. Systems completion and integration: whether completion, verification, integrated testing and handover are organized by system, with defined stage-gates and evidence (ICXA-20101 cl. 7, 9 and Annex B).
1. Operational readiness: whether the receiving organization is developing People, Organization, Asset and Systems & Processes capability in time, and whether Transfer of Operational Control, start-up and ramp-up are governed (ICXA-20201 cl. 4, 7 and 9).
1. Readiness evidence maturity: whether evidence requirements were set in advance, and whether evidence is controlled, current, traceable and relevant rather than a measure of activity (ICXA-10002 cl. 4 to 7; ICXA-20201 cl. 8).
1. Transition risk and corrective action: whether readiness risks, conditions and deferred work are recorded and owned, and whether shortfalls are corrected.
5. Assessment logic
Assessment begins before financial close and follows the maturity the Standards expect at each point in the lifecycle:
1. Before financial close and through engineering, prove the path. The Adviser establishes a readiness baseline and assesses whether a credible, accountable and resourced path to readiness exists: stage-gates defined, readiness criteria and evidence needs set in advance, roles and independence assigned. It proposes the Readiness Maturity Path for the lenders to agree before initial disbursement.
1. During construction, prove the progression. The Adviser assesses whether readiness evidence and capability are developing when the Readiness Maturity Path requires, and whether Readiness Milestones are met.
1. From commissioning to operations, prove the condition. Before each transition stage-gate the Adviser assesses whether the readiness conditions for the systems and operational boundaries concerned have been demonstrated, and through ramp-up whether outstanding conditions are being closed.
A readiness condition that the Readiness Maturity Path does not yet require is not yet due and is not a deficiency. Missing or inaccessible evidence is insufficient evidence and is not a finding of technical failure. The Adviser shall distinguish, for each criterion, a condition demonstrated, a confirmed deficiency, insufficient evidence, not yet due, not applicable (with reasons) and outside scope, and shall not combine findings into a score or allow any summary to obscure a material unresolved condition. For each conclusion the Adviser shall state the evidence confidence it supports, and shall distinguish evidence that the required capability exists from evidence that only records that an activity was completed.
6. Deliverables
1. Readiness baseline report before initial disbursement, with the proposed Readiness Maturity Path, the readiness criteria designated as material, and any Readiness Milestones, with reasons. Where the Appointment starts after financial close, a baseline at the current stage stating what can no longer be tested.
1. Readiness section in each periodic report, opening with an executive summary that answers in words: whether readiness maturity is progressing as required; which material readiness conditions are behind their required state, unsupported by evidence or deficient; what could affect the planned transition or operating assumptions; what changed since the previous review; which capital-release conditions have or have not been demonstrated; and what actions or lender decisions are required. It is supported by an evidence register and an exceptions schedule.
1. Drawdown readiness statement with each drawdown certificate, stating which capital-release conditions due at that drawdown have or have not been demonstrated.
1. Transition stage-gate reports before each transition stage-gate the Readiness Maturity Path identifies, such as Ready for Start-Up and Transfer of Operational Control of each critical system.
1. Completion and stabilization report at Project Completion and, if mandated, at the end of stabilization.
1. Referral notes to the Client within [3] Business Days where a material readiness condition has not been demonstrated or a finding may affect a capital-release decision, stating the evidence position, the potential consequence and the options the Adviser sees.
The Adviser may use its own methods, tools and formats. Its conclusions are stated within its mandate: it shall not state that the Project is 'ready', shall not recommend approval or refusal of a drawdown, and shall not certify readiness unless the Appointment requires a specified certificate. Capital-release decisions rest with the Client and the lenders under the financing documents. Start-up and Transfer of Operational Control remain decisions of the Borrower and operator.
7. Evidence, roles and independence
Readiness evidence is produced by the project in accordance with the roles, responsibilities and independence the ICxA Standards define: execution evidence owners for systems completion (ICXA-20101 cl. 6.1), the operational readiness role and receiving operational authority (ICXA-20201 cl. 5.1), independent evaluation of evidence sufficiency by an Outcome Auditor and authorization by an Outcome Director (ICXA-10001 cl. 5.3 and 8.2). The Adviser reviews that evidence and the project's evaluation and authorization records; it does not produce readiness evidence, take part in the project's readiness decisions, or act as the project's Outcome Auditor.
The Client shall procure through the financing documents that the Borrower gives the Adviser access to readiness evidence, personnel and site within [10] Business Days of request. The Adviser shall keep a dated record of requests and report criteria as insufficient evidence where access was not given.
8. Competence and delivery capability
Assessing readiness requires leadership experience of taking capital projects through the transition from construction to operations, not commissioning experience alone. The Adviser shall assign a readiness lead holding the ICxA Commissioning Project Manager (CxPM) or Operational Readiness Strategist (ORS) credential or higher, and preferably the Outcome Auditor (OA) or Outcome Director (OD) credential, or demonstrably equivalent experience. The Adviser shall state the competence basis of each person assigned.
The Adviser may build internal capability to fulfil the readiness mandate, or engage an ICxA Operating Partner. Either way the Adviser remains responsible to the Client under the Appointment.
The Adviser and its personnel shall be independent of the Borrower, the EPC contractors, the operator and the technology licensors, and shall disclose any actual or potential conflict before appointment and during the services.
9. Material change and escalation
On notice of a Readiness Material Change the Adviser shall identify the affected readiness criteria within [5] Business Days, reassess them in the next report or sooner if the Client asks, and where appropriate propose a revised Readiness Maturity Path, which takes effect only when agreed by the Client. Where a material criterion is deficient, unsupported or behind the Readiness Maturity Path, or a Readiness Milestone is missed, the Adviser shall issue a referral note.
10. Limitations
Nothing in this addendum requires legal opinions, verification of the financial model, additional site testing or any guarantee of operational performance unless separately agreed. The additional effort is [to be proposed by the Adviser]. Deliverables, reliance, confidentiality and liability are governed by the Appointment.
Schedule 1 — Readiness criteria
For each criterion, the Adviser assesses the state of the relevant readiness conditions the project has defined, at the stage-gate concerned, against the project's readiness criteria and the ICxA clauses cited. [N] marks a normative requirement of the cited Standard, [G] guidance or informative text, and [P] an addition made by this pack for financing purposes.
A. Outcome and financial alignment
	Criterion
	What the Adviser assesses
	ICxA reference

	LRC-A01 Operating outcomes and financing-case assumptions
	The intended operating outcomes (capacity, output, availability, quality, ramp-up profile, operating cost basis) are defined, traceable to project requirements, and consistent with the assumptions in the financing case.
	ICXA-10001 cl. 4.1 [N]; ICXA-10001 cl. 6.2 [N]; ICXA-20201 cl. 4.4 a) [N]; Pack [P]

	LRC-A02 Transition milestones distinguished and connected
	Construction completion, commissioning stage-gates, start-up, transfer of operational control, commercial operation and the financing completion date are separately defined, sequenced by system, and connected to the schedule and financing milestones.
	ICXA-10001 cl. 6.3 [N]; ICXA-10001 cl. 6.5 [N]; ICXA-20101 cl. 9.1 [N]; ICXA-20101 cl. 9.2.2 [N]; ICXA-20101 cl. 6.8 [G]

	LRC-A03 Readiness integrated into the project schedule
	Systems completion and operational readiness activities, constraints, reviews and decision points are integrated with the project master schedule so that readiness slippage is visible to decision-makers when it occurs.
	ICXA-20101 cl. 10.1 [N]; ICXA-20101 cl. 11.7 [N]; ICXA-20201 cl. 6.7 [N]

	LRC-A04 Control of changes to the outcome and readiness basis
	Changes that affect outcomes, operating assumptions, system boundaries or readiness conditions are evaluated before they are relied on, and outcome or acceptance criteria are not relaxed to accommodate readiness shortfalls.
	ICXA-10001 cl. 6.2 [N]; ICXA-10001 cl. 6.4 [N]; ICXA-20101 cl. 7.5 [N]; ICXA-20201 cl. 7.1.5.3 [N]



B. Integrated delivery and interface accountability
	Criterion
	What the Adviser assesses
	ICxA reference

	LRC-B01 Division of responsibility across contracts
	Responsibilities for systems completion, testing, operational readiness, handover and post-handover support are allocated across EPC contractors, suppliers, the owner and the operator without gaps or overlaps.
	ICXA-20101 cl. 10.4 [N]; ICXA-20101 cl. 11.2 f) [N]; ICXA-20101 cl. 6.6 [N]

	LRC-B02 Cross-contract interfaces and dependencies
	Interfaces that affect system readiness and verification are identified, assigned, tracked and resolved, including dependencies between contracts, vendors, utilities and the operator.
	ICXA-20101 cl. 11.8 [N]; ICXA-10001 cl. 8.4 f) g) [N]; ICXA-20201 cl. 6.7 [N]

	LRC-B03 Readiness decision authority and independence
	The project has defined who prepares readiness evidence, who reviews it, and who decides progression at each stage-gate, with review separated from those responsible for delivery and from schedule pressure.
	ICXA-10001 cl. 5.3 [N]; ICXA-20101 cl. 6.1 [N]; ICXA-20101 cl. 6.2 [N]; ICXA-20201 cl. 5.1 [N]; ICXA-20201 cl. 5.2 [N]

	LRC-B04 Escalation and dispute resolution for readiness issues
	Readiness gaps, evidence disputes and authority conflicts have a defined escalation route that reaches decision-makers in time, including where several contracting parties are involved.
	ICXA-20101 cl. 6.5 [N]; ICXA-20201 cl. 5.4 [N]; ICXA-20201 cl. 5.5 [N]



C. Systems completion and integration
	Criterion
	What the Adviser assesses
	ICxA reference

	LRC-C01 Systems completion strategy and plan
	A system-based strategy and plan for systems completion, verification and handover exist, set out milestones, resources, risks and tailoring, and are maintained as the project develops.
	ICXA-20101 cl. 10.1 [N]; ICXA-20101 cl. 10.2 [N]; ICXA-20101 cl. 10.7 [N]; ICXA-20101 cl. 11.2 [N]

	LRC-C02 System breakdown and boundaries
	A system breakdown structure with defined system boundaries is baselined, used as the index for completion, testing and handover records, and kept under change control.
	ICXA-10001 cl. 4.3 e) [N]; ICXA-20101 cl. 7.1 [N]; ICXA-20101 cl. 7.2 [N]; ICXA-20101 cl. 7.5 [N]; ICXA-20101 cl. 11.6 [N]

	LRC-C03 Stage-gates and minimum evidence sets
	Systems completion stage-gates (at least Construction Completion, Ready for Dynamic Commissioning, Ready for Start-Up and System Handover, or documented equivalents) have defined entry criteria and minimum evidence, and progression is not based on percentage complete alone.
	ICXA-20101 cl. 9.2.2 [N]; ICXA-20101 cl. 9.4 [N]; ICXA-20101 cl. 6.7 [N]; ICXA-20101 cl. Annex B [N]

	LRC-C04 Vendor and procurement readiness
	Vendor testing, documentation, support during commissioning, spares and warranty obligations needed for readiness are defined in procurement and tracked to delivery.
	ICXA-20101 cl. 10.5 [N]; ICXA-20101 cl. 12.8 [N]; ICXA-20101 cl. 13.6 [N]

	LRC-C05 Integrated testing and start-up preparation
	Verification and test plans, integrated and dynamic test procedures, control and safety system testing, and a start-up readiness review are prepared in time for the systems concerned.
	ICXA-20101 cl. 12.2 [N]; ICXA-20101 cl. 12.5 [N]; ICXA-20101 cl. 12.6 [N]; ICXA-20101 cl. 9.2.2 d) [N]

	LRC-C06 Deficiency management
	Outstanding work and deficiencies are classified by their effect on stage-gate progression, tracked to closure with evidence, and not downgraded or deferred solely to protect schedule.
	ICXA-20101 cl. 12.9 [N]; ICXA-20101 cl. 9.3 [N]; ICXA-10001 cl. 8.5 [N]



D. Operational readiness
	Criterion
	What the Adviser assesses
	ICxA reference

	LRC-D01 Readiness charter, plan and envelope
	An operational readiness charter and plan (or equivalent) define the readiness scope, operating assumptions, criteria, reviews and decision authority, mapped to the system breakdown.
	ICXA-20201 cl. 4.3 [N]; ICXA-20201 cl. 4.4 [N]; ICXA-20201 cl. 6.1.1 [N]; ICXA-20201 cl. 6.1.2 [N]

	LRC-D02 People
	The workforce model, recruitment, training and demonstrated competence of operating and maintenance staff progress in time to support start-up and operation, including capacity for abnormal and emergency conditions.
	ICXA-20201 cl. 7.1.2.1 [N]; ICXA-20201 cl. 7.1.2.2 [N]; ICXA-20201 cl. 7.1.2.3 [N]; ICXA-20201 cl. 7.1.2.4 [N]; ICXA-20201 cl. 6.4 [N]; ICXA-20101 cl. 13.4 [N]

	LRC-D03 Organization
	Operating governance, decision authority, operational control arrangements and emergency preparedness are defined and shown to work before operational control is assumed.
	ICXA-20201 cl. 7.1.3.1 [N]; ICXA-20201 cl. 7.1.3.2 [N]; ICXA-20201 cl. 7.1.3.3 [N]; ICXA-20201 cl. 7.1.3.4 [N]

	LRC-D04 Asset
	Asset condition, maintainability, spares, consumables, utilities and external supply commitments needed to operate are identified and in place for the systems being transferred.
	ICXA-20201 cl. 7.1.4.1 [N]; ICXA-20201 cl. 7.1.4.2 [N]; ICXA-20201 cl. 7.1.4.3 [N]; ICXA-20101 cl. 13.2 e) [N]

	LRC-D05 Systems and processes
	Operating and maintenance procedures, enabling systems (maintenance management, operating data, document control) and configuration control are built and usable by the people who rely on them before transfer.
	ICXA-20201 cl. 7.1.5.1 [N]; ICXA-20201 cl. 7.1.5.2 [N]; ICXA-20201 cl. 7.1.5.3 [N]; ICXA-20201 cl. 6.5 [N]

	LRC-D06 Transfer of operational control, start-up and ramp-up
	Criteria and records for transfer of operational control, operational acceptance, start-up support, ramp-up and stabilization are defined, and transfer occurs only after a recorded readiness review and acceptance by the receiving authority.
	ICXA-20201 cl. 9.1 [N]; ICXA-20201 cl. 9.3 [N]; ICXA-20101 cl. 13.1 [N]; ICXA-20101 cl. 13.2 [N]; ICXA-20101 cl. 13.3 [N]; ICXA-10002 cl. A.6 [G]; ICXA-20200 cl. Annex B [G]



E. Readiness evidence maturity
	Criterion
	What the Adviser assesses
	ICxA reference

	LRC-E01 Evidence requirements defined in advance
	For each stage-gate and transition milestone the project defines in advance what evidence is required, proportionate to consequence and irreversibility, before that evidence is produced.
	ICXA-10002 cl. 4 e) [N]; ICXA-10002 cl. 5 [N]; ICXA-10002 cl. 6 [N]; ICXA-10001 cl. 8.2 [N]

	LRC-E02 Evidence control, traceability and currency
	Readiness evidence is controlled, current, traceable to the system and stage-gate it supports, and retrievable for review by the LTA.
	ICXA-20101 cl. 8.3 [N]; ICXA-20101 cl. 8.4 [N]; ICXA-20101 cl. 8.6 [N]; ICXA-20201 cl. 8.1 [N]; ICXA-20201 cl. 8.2 [N]

	LRC-E03 Sufficiency not substituted by volume or progress
	Readiness conclusions, the project's and the LTA's, rest on evidence that is relevant to the decision, not on document volume, checklist completion, dashboards or activity status.
	ICXA-10002 cl. 4 h) [N]; ICXA-10002 cl. 7 [N]; ICXA-20201 cl. 8.2 [N]; ICXA-20101 cl. 6.7 [N]; ICXA-10001 cl. 8.3 [N]

	LRC-E04 Progressive readiness reviews
	The project holds readiness reviews at planned points, records a recommendation (proceed, proceed with conditions, or hold) and reports hold outcomes.
	ICXA-20101 cl. 6.7 [N]; ICXA-20201 cl. 8.4 [N]; ICXA-20201 cl. 9.1 [N]



F. Transition risk and corrective action
	Criterion
	What the Adviser assesses
	ICxA reference

	LRC-F01 Readiness risks identified and owned
	Readiness risks are identified early, expressed as operational and transition consequences, assigned to owners, and kept current in the project risk register.
	ICXA-10001 cl. 6.1 [N]; ICXA-20201 cl. 6.2 [N]; ICXA-20201 cl. 8.3 [N]; ICXA-20101 cl. 6.4 [N]

	LRC-F02 Conditions, exceptions and deferred work
	Where progression proceeds with conditions or deferred work, each item is recorded with owner, due date and closure evidence, safety- or regulatory-critical items are not deferred past the relevant gate, and deferred items are visible to lenders.
	ICXA-20101 cl. 6.4 [N]; ICXA-20101 cl. Annex B.1 [N]; ICXA-20101 cl. 13.3 a) [N]; ICXA-20201 cl. 8.3 [N]; ICXA-10001 cl. 8.5 [N]

	LRC-F03 Corrective action and closure
	Readiness deficiencies and LTA findings receive corrective action plans with owners and deadlines, and closure is verified with evidence.
	ICXA-20201 cl. 8.3 [N]; ICXA-20201 cl. 10.3 [N]; ICXA-20101 cl. 12.9 [N]

	LRC-F04 Ramp-up and stabilization monitoring
	After transfer, ramp-up and stabilization performance, early-life defects and open readiness actions are monitored against defined targets within the LTA's agreed mandate.
	ICXA-20201 cl. 9.3 [N]; ICXA-20101 cl. 13.6 [N]; ICXA-20200 cl. Annex B.4 [G]
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How the lender's readiness requirements link to the project lifecycle
Example sequence. Each project defines its own stage-gates, readiness criteria and readiness conditions under the ICxA Standards.

Assessment focus

Prove the path Prove the progression Prove the condition

credible, accountable, resourced

maturity keeping pace

demonstrated for each system

Example stage-gates

(ICxA Standards)

O O O O O O O
O O O O O O O
FEED Design and Procurement Construction Ready for ~ System Handover / Stabilization
outcome engineering Completion Start-Up Transfer of
Operational Control
drawdowns

Lender milestones

3 }

Financial close
(initial disbursement)

L g -

Project Release of
Completion completion
support

What the lender
requires

Readiness baseline
and agreed Readiness

(before financial close)

Maturity Path

Readiness findings with each
LTA review and drawdown;
dated Readiness Milestones

Readiness conditions
demonstrated at
transition gates

Completion and
stabilization
evidence

Readiness maturity is assessed progressively from before financial close through to stabilization

References: stage-gates ICXA-10001 cl. 6.3 and ICXA-20101 cl. 9.2; evidence need ICXA-10002; operational readiness reviews and transfer ICXA-20201cl. 9.




